## Bugs
Bug ID | Bug Description | Steps To Reproduce | Severity | Date Found | Playtest ID | Date Fixed | Fix Description
1 | Leave Session Button Not Working | Open pause menu and press leave game button | High | 2024-07-23 | 1 | 2024-07-24 | Use server travel on session destroyed delegate
2 | Can Tag Crosshair Persists After Target Leaves Game | Aim at untagged player as tagger and have player leave game | Low | 2024-07-24 | 2

## Playtests
Playtest ID | Playtest Focus | Date | Users Present
1 | Game Modes Refactor | 2024-07-23 | Rajan, Will
1 | Leaave Game Button | 2024-07-24 | Rajan, Will